## 1. Cover & Legend
Dash Logistic — Q3 2026 Prioritization · September Focus
Squads: 4W · Scheduled Instant · X-dock ¦ PM: Isumi Karina ¦ Rev 3 · 31 Aug 2026
Purpose | Consolidate Q3 next-step work across three squads into one prioritized, month-phased backlog. September = the committed slate. Everything else flows October → Q4. Each squad has its own priority tab, sorted so September items surface first. Rev 3 folds in the 31 Aug internal-team meeting + whiteboard.
How it's organized | One priority tab per squad. Reasoning is inline (the 'Reasoning & sequencing' column) — no separate rationale tab. Driver-App push notifications stay on Tab 6. Open questions / decisions-needed are on Tab 7. Completed post-release improvements are excluded (already shipped).
Goal horizon | Short / Medium / Side — the 31 Aug internal-meeting framing. Short = do now, API + x-dock-100% urgent. Medium = network capability next (transit, return dispatch). Side = opportunistic side-quests (COD, leave-at-outlet, timeline media). Defined by that meeting for X-dock; applied by analogy to 4W / SI.
Surfaces | Mithril = internal Ops dashboard · Dash Link = client portal · Driver App = driver mobile app · Back Office / Web = ops tooling · Integration = external client API / sandbox · WA = WhatsApp automation.
Priority tiers | P0 = must-ship this cycle (blocks a live launch / fraud / data-loss) · P1 = high (unblocks scale or removes daily Ops pain) · P2 = important, schedulable · P3 = nice-to-have / deferred.
Month phasing | Sep = committed September slate. Oct / Nov = next in Q3. Q4 = large-scope, blocked-on-business, or exploratory. TBC = awaiting business/leads decision before it can be scheduled.
RICE scoring | Reach (1-5): trips/users touched per week. Impact (0.5,1,2,3): data loss/fraud=3; daily Ops friction=2; polish=1; edge=0.5. Confidence (%): certainty the fix delivers the impact. Effort (person-weeks): BE+FE+Mobile combined. Score = (Reach × Impact × Confidence) ÷ Effort. Higher = ship earlier.
Readiness | 'Prototype + PRD' = buildable now · 'Prototype only'/'PRD only' = one artifact missing · 'Draft' = early · 'None — needs PRD/prototype' = requirement gathering first · 'Spike/feasibility' = go/no-go pending. NOTE: every 4W September item still needs PRD + prototype — September for 4W is scope-and-build (write those PRDs in the first days of the month).
Sort rule | Each squad tab is sorted by Target month (Sep → Q4), then Priority (P0 → P3), then Score DESC. Edit RICE inputs and the Score column recalculates; re-sort after edits.
Ownership | PM = Isumi Karina across all items. Engineer = 'TBC' (to be assigned; manpower split for short goals is an open item — Tab 7). The 31 Aug meeting named Yogi for R&D / API integration — noted in reasoning, not yet locked in the Engineer column.
Sources | (1) 4W EXIM Post-Release Recap (RICE reused). (2) Meeting summary 28 Aug 2026. (3) Meeting summary 31 Aug 2026 + whiteboard. (4) Feature & Performance Review, Agustus W2. Where they disagree, the more recent meeting wins; open decisions live on Tab 7.
Rev 3 (31 Aug) | X-dock: added x-dock-100% umbrella, API integration platform + sandbox, Mark-Stock removal / waiting-time-per-stop, outlet-hours master data, inter-hub transit, return dispatch, timeline media download; expanded Retry into Retry + Fail-conditions + SLA-defense. 4W: added Ops input fields (DN Customer, FO, AGL Route Code); enriched UJP (Nexus / grounds / spec-control, master-data research). Added Tab 7 Open Questions.
Rev 2 (31 Aug) | Removed as done: X-dock Adjust No. Invoice; SI Phase 2 WA confirm loop & Calendar metrics. Removed as cancelled: SI NCS API integration. Merged: SI template-standardize + AI header-checker (one item).
Priority swatches
P0 | Must-ship this cycle
P1 | High
P2 | Important, schedulable
P3 | Nice-to-have / deferred
Month swatches
Sep | Committed September slate
Oct | Next — October
Nov | November
Q4 | Later / large-scope / blocked
TBC | Awaiting business decision
Goal-horizon swatches
Short | Do now (31 Aug short goals)
Med | Network capability next (medium goals)
Side | Opportunistic side-quest

## 2. September Commitment
Dash Logistic Q3 — September Commitment (all squads)
The committed September slate across all three squads. Full detail & RICE live in each squad tab. PM: Isumi Karina.
Squad | # | Item | Priority | Goal | Readiness | Engineer | Confidence to land Sep | Note / dependency
X-dock | XD-02 | Retry Shipment + Fail Conditions + SLA defense | P0 | Short | None — needs PRD/prototype | TBC | Medium | XD-01, Fail-condition SOP
X-dock | XD-01 | X-dock 100% — shipment + route, last-mile, failed conditions | P0 | Short | In progress — needs PRD | TBC | High | —
X-dock | XD-07 | COD Phase 1 — reconciliation | P0 | Side | Prototype + PRD ✓ | TBC | High | —
X-dock | XD-03 | New API integration platform — sandbox, API key, webhook, simulation | P0 | Short | Prototype/simulation exists; timeline revising | TBC | Medium | Sandbox tech spec
X-dock | XD-06 | Multi-invoice per visit + scan blank document / leave at outlet | P1 | Side | Prototype + PRD ✓ | TBC | High | Mobile engineer slot
X-dock | XD-08 | Timeline media download | P2 | Side | None — needs PRD (small) | TBC | Medium | —
Scheduled Instant | SI-02 | Pricing per shift | P0 | Short | Prototype + PRD ✓ (pending business) | TBC | Medium | Business pricing decision
Scheduled Instant | SI-01 | Exception blast WhatsApp — Noovoleum | P0 | Short | Spike | TBC | Medium | —
4W | NS-DA-01 | Move completed shipment from Beranda → Riwayat | P0 | Short | None — needs PRD/prototype | TBC | Medium | —
4W | NS-MTH-01 | Cancel Shipment (human-error from UJP) | P0 | Short | None — needs PRD/prototype | TBC | Medium | UJP bridge (import-only)
4W | NS-MTH-02 | Mark as Completed / Mark as Failed (Ops override) | P0 | Short | None — needs PRD/prototype | TBC | Medium | —
4W | 4W-FLD | Add Ops input fields: DN Customer, FO, AGL Route Code | P0 | Short | None — needs PRD (small) | TBC | Medium | —
4W | NS-DL-01 | EXIM Import/Export tagging (consumer) | P1 | Short | None — needs PRD (dep NS-MTH-03) | TBC | Medium | NS-MTH-03 (Mithril tag)
4W | NS-MTH-03 | EXIM Import/Export tagging | P1 | Short | None — needs PRD/prototype | TBC | Medium | —
4W | NS-DA-03 | Push Notifications (full set — see Tab 6) | P1 | Short | None — needs PRD (Wave 1) | TBC | Medium | NS-MTH-01, NS-MTH-02

## 3. 4W — Priority
Dash Logistic Q3 — 4W — Priority
4W (roda-4) — pilot AGL Patimban. RICE reused from the Post-Release Recap. NEW: Ops input fields (DN Customer, FO, AGL Route Code). All September items still need PRD/prototype — September is scope-and-build.
# | Surface | Item | Why (problem it solves) | Reach (1-5) | Impact (0.5-3) | Confidence (%) | Effort (pw) | Score | Priority | Target month | Goal horizon | Readiness | PM | Engineer | Depends on | Reasoning & sequencing
NS-DA-01 | Driver App | Move completed shipment from Beranda → Riwayat | Completed shipments stay on Beranda and 'Mulai Pengiriman' can be re-triggered on a done trip → duplicate proof rows / status confusion. | 5 | 3 | 90% | 1 |  | P0 | Sep | Short | None — needs PRD/prototype | Isumi Karina | TBC | — | P0 despite being a 'next-phase' item — a live bug surface: drivers can re-fire a completed trip, producing duplicate proof and a confused status timeline. 1pw of Mobile work; makes the interim DA-06 'hide button' hack the real fix. Top RICE score, ships with the September P0 cluster.
NS-MTH-01 | Mithril | Cancel Shipment (human-error from UJP) | When UJP creates a shipment with the wrong client/lane, Ops has no way to undo it — it pollutes pilot metrics and pushes a bad workflow to drivers. | 4 | 3 | 85% | 1 |  | P0 | Sep | Short | None — needs PRD/prototype | Isumi Karina | TBC | UJP bridge (import-only) | P0 because UJP human-error is a known-recurring issue. Small state transition + audit reason. Must ship paired with push PN-02 — don't release one without the other or drivers will run cancelled trips.
NS-MTH-02 | Mithril | Mark as Completed / Mark as Failed (Ops override) | When a driver phone dies or loses connectivity mid-trip the shipment is stuck IN_DELIVERY; Ops needs a manual terminal-state override (reason + audit log) so billing & tracking can close. | 4 | 3 | 85% | 1 |  | P0 | Sep | Short | None — needs PRD/prototype | Isumi Karina | TBC | — | P0 because 'driver phone dead' is a real EXIM pattern (long trips, Patimban dead zones). Without it, shipments live IN_DELIVERY forever and billing can't close. Pair with push PN-03.
4W-FLD | Mithril / Dash Link / Driver App | Add Ops input fields: DN Customer, FO, AGL Route Code | Capture and display the fields Ops actually needs on 4W shipments — DN Customer, FO, and AGL Route Code — which are missing from the current Create Shipment / workflow forms. | 5 | 2 | 85% | 1 |  | P0 | Sep | Short | None — needs PRD (small) | Isumi Karina | TBC | — | Raised by Ops after the internal meeting: the 4W flow lacks the input fields Ops needs to operate and reconcile — DN Customer, FO, and AGL Route Code. Add them to Create Shipment (Mithril), carry through to Shipment details / Dash Link display and the driver flow where relevant, and include them in the print/export templates. Small but blocks clean 4W operations at rollout → September P0. Keys off the AGL Patimban pilot's document/route conventions.
NS-DL-01 | Dash Link | EXIM Import/Export tagging (consumer) | Client-facing filter / column on Dash Link that consumes the Mithril direction tag — no independent work beyond FE render + filter. | 5 | 2 | 85% | 0.5 |  | P1 | Sep | Short | None — needs PRD (dep NS-MTH-03) | Isumi Karina | TBC | NS-MTH-03 (Mithril tag) | TOP quick-win (score 17): 0.5pw because Mithril emits the tag once NS-MTH-03 lands — Dash Link only renders + filters. Client (SwipeRX/AGL Ops) has directly asked to filter by direction. Ship together with, or immediately after, NS-MTH-03 in September.
NS-MTH-03 | Mithril | EXIM Import/Export tagging | Make delivery direction a first-class tag (today it's inferred from stop pattern). Unlocks the Dash Link filter, tracking labels, and Ops reports. | 5 | 2 | 90% | 1.5 |  | P1 | Sep | Short | None — needs PRD/prototype | Isumi Karina | TBC | — | P1 not P0 — the engine already infers direction, so nothing breaks without it. But it's the unlock for NS-DL-01, NS-DA-02 and future reporting, so schedule it in September right after the P0 cluster.
NS-DA-03 | Driver App | Push Notifications (full set — see Tab 6) | Zero push today → a driver only learns about a trip by opening the app. Harms on-time gate-in and adds Ops phone-call load. See Tab 6 for the catalogue and per-notif priority. | 5 | 3 | 80% | 2.5 |  | P1 | Sep | Short | None — needs PRD (Wave 1) | Isumi Karina | TBC | NS-MTH-01, NS-MTH-02 | High reach × high impact × moderate effort (2.5pw). Split into two waves (Tab 6): Wave 1 ships in September with the P0 cluster (PN-02/PN-03 depend on Cancel/Override landing first); Wave 2 follows in October.
4W-NEG | Mithril / Driver App | Negative-scenario handling (failure & exception flows) | Model the non-happy paths end-to-end: delivery failed, partial delivery, return-to-origin, exception at gate. Today only the happy path is fully handled. | 4 | 3 | 60% | 2.5 |  | P1 | Oct | Short | None — needs PRD | Isumi Karina | TBC | — | A gap surfaced after the pilot release. No PRD or prototype yet (confidence 0.60) — requirement gathering first, then build. Aligns with the X-dock 'failed condition' work (shared fail-reason + evidence patterns). October so it doesn't compete with the September P0 cluster.
NS-DA-05 | Driver App | Local storage + auto-delete (or dedicated logistic app) | Driver phone dies before evidence syncs → billing evidence lost. Local persistence with server-side reconciliation on reconnect. Alternative: a dedicated Dash Logistic app. | 4 | 3 | 65% | 4 |  | P1 | Oct | Med | Needs arch decision | Isumi Karina | TBC | Mobile arch decision (in-app vs new app) | P1 but scored below Push: 4pw and it needs an architecture call (enhance the shared app vs. spin a dedicated Dash Logistic app). 1-week spike first, then decide. High impact (prevents evidence loss = prevents billing loss) but confidence 0.65 until the arch decision → October.
NS-DA-02 | Driver App | EXIM Import/Export tagging (label on trip card) | IMPORT / EXPORT badge on Beranda + stepper header — reduces confusion on mixed-lane days. | 5 | 1 | 85% | 0.5 |  | P2 | Oct | Side | None — needs PRD (dep NS-MTH-03) | Isumi Karina | TBC | NS-MTH-03 (Mithril tag) | 0.5pw, purely visual. Impact 1 (not 2): drivers rarely mix directions in one day, so it's a clarity win. Piggyback on the Mithril tag rollout in October.
NS-DA-04 | Driver App | Infinix OS: bypass allow-setting workaround | Infinix devices block camera/storage permissions by default, preventing Driver App use for a subset of drivers. Vendor-specific fix. | 2 | 3 | 70% | 1.5 |  | P2 | Oct | Side | Investigation | Isumi Karina | TBC | — | P2 despite high per-user impact — reach is small (only drivers on that OEM). Ship when an Infinix driver is confirmed in the pilot roster, otherwise defer within October.
4W-TRK | Mithril / Invoices | Tracking invoice 4W | Import/track 4W invoices by Surat Jalan keyword (4W has no barcode), integrated into the existing Invoices feature. | 4 | 2 | 60% | 2 |  | P2 | Q4 | Med | None — post-Sept scope | Isumi Karina | TBC | Invoices feature (existing) | Next-phase item from the feature review, scoped after the September rollout so decisions are based on real usage. Connects 4W into the existing Invoices feature; no barcode means it keys off the SJ number.
NS-MTH-04 | Mithril / Nexus | Full sistem UJP — migrate UJP → Mithril (native module) | Bring UJP native into Mithril (today it's a separate system in Nexus with an import-only bridge). Removes double-entry, closes the fraud loop, and enables end-to-end finance reporting. | 5 | 3 | 75% | 6 |  | P2 | Q4 | Side | None — needs PRD + master-data research | Isumi Karina | TBC | spec control + 'grounds', Basecamp API | Largest scope item (6pw) and the user-flagged 'sistem UJP'. 31 Aug confirmed UJP as the CORE for 4-wheels and prioritized it over P&L (P&L can stay in the existing system for now). UJP lives in Nexus and must integrate with spec control and 'grounds' (which own auto-P&L + control); upload needs master data from several sources → research first. P&L / gross-margin / payroll / 'kois' automation is a later side-quest once all clients use full shipment. Schedule after the pilot is stable.
4W-FLT | Driver App / Fleet | Integrasi Fleet — pre-trip QR scan | Driver scans a vehicle QR at pre-trip so they take the assigned vehicle; the scan result syncs to the Fleet system. | 4 | 2 | 55% | 2.5 |  | P2 | Q4 | Med | None — post-Sept scope | Isumi Karina | TBC | Fleet system | Cross-system dependency on Fleet. Next-phase, scoped after the September rollout review. Ensures driver-vehicle assignment integrity; lower confidence until the Fleet-side contract is confirmed.

## 4. Scheduled Instant — Priority
Dash Logistic Q3 — Scheduled Instant — Priority
Scheduled Instant — rider scheduling & shipment intake. September = Noovoleum WA exception + pricing per shift.
# | Surface | Item | Why (problem it solves) | Reach (1-5) | Impact (0.5-3) | Confidence (%) | Effort (pw) | Score | Priority | Target month | Goal horizon | Readiness | PM | Engineer | Depends on | Reasoning & sequencing
SI-02 | Mithril / Back Office | Pricing per shift | Price per shift (dedicated manpower / daily-flat) instead of per-trip only. | 4 | 2 | 80% | 1.5 |  | P0 | Sep | Short | Prototype + PRD ✓ (pending business) | Isumi Karina | TBC | Business pricing decision | Prototype + PRD ready; the only blocker is the commercial pricing decision. Raise it in the Mon 1 Sept priority meeting with Pak Harina; once decided it lands in September. Unlocks correct billing for dedicated-manpower clients.
SI-01 | WA / Backend | Exception blast WhatsApp — Noovoleum | Client-specific exception to the WhatsApp blast rules for Noovoleum riders. | 2 | 2 | 70% | 1 |  | P0 | Sep | Short | Spike | Isumi Karina | TBC | — | Client commitment, currently being spiked by engineering. Small in scope but client-blocking, so it rides with the September P0 slate.
SI-03 | Mithril / Schedule | Filter cari per rider (POV rider) | See every client a single rider is assigned to on a given day (this view lives today in an Ops-built internal tool). | 3 | 1 | 75% | 1 |  | P1 | Oct | Side | PRD only | Isumi Karina | TBC | — | Replaces a manual Ops workaround with a native view. Useful but not launch-blocking → October.
SI-04 | Web / Back Office (+AI spike) | Standardize bulk-upload template + AI header-checker (feasibility) | One initiative, two paths to the same goal — let clients self-upload orders without the Ops team, cutting human error. Path A (committed): standardize the bulk-upload template header. Path B (spike): an AI that auto-validates arbitrary/dynamic client CSV headers. | 4 | 2 | 55% | 2.5 |  | P1 | Oct | Side | Draft template (AI = feasibility spike) | Isumi Karina | TBC | Speaker 1 CSV analysis | Two solutions to one problem, tracked as one item; appears on the 31 Aug board as side-quest 'shipment AI upload?'. A draft template exists (Path A). The 28 Aug meeting judged the AI checker (Path B) very high-effort — client templates are dynamic, manual validation is still needed up front, supporting data is hard to pull. Decision: commit to the template first; run the AI checker only as a time-boxed spike whose go/no-go rests on Speaker 1's analysis of NCS's sample CSV (Tab 7). Confidence 0.55: committed scope clear, AI upside unproven.
SI-05 | TBC | Sayurbox — Tender Sistem | System tender for Sayurbox. | 3 | 2 | 30% | 3 |  | P3 | TBC | Side | TBC — business / leads | Isumi Karina | TBC | Business & Leads scope | Detail and context are incomplete — still TBC with Business & Leads. Cannot be scoped or scheduled until they define the requirement, so it sits outside the month plan for now.

## 5. X-dock — Priority
Dash Logistic Q3 — X-dock — Priority
Cross-docking — 31 Aug internal meeting: Short goals (x-dock 100%, retry+fail-conditions, API platform), Medium goals (transit, return dispatch), Side quests (COD, leave-at-outlet, timeline media).
# | Surface | Item | Why (problem it solves) | Reach (1-5) | Impact (0.5-3) | Confidence (%) | Effort (pw) | Score | Priority | Target month | Goal horizon | Readiness | PM | Engineer | Depends on | Reasoning & sequencing
XD-02 | Mithril / Driver App | Retry Shipment + Fail Conditions + SLA defense | When a delivery can't complete (outlet/pharmacy closed, no time left), the driver logs a recorded fail reason with field evidence instead of a new shipment being created blindly. Fail conditions + evidence let Dash defend its SLA against unfair client penalties. | 5 | 3 | 70% | 2.5 |  | P0 | Sep | Short | None — needs PRD/prototype | Isumi Karina | TBC | XD-01, Fail-condition SOP | The 31 Aug meeting sharpened this into three linked parts: (a) Retry instead of blind re-create; (b) Fail Conditions (time not possible, outlet closed, …) each needing field evidence, e.g. a photo of the closed outlet; (c) SLA rebuttal — a valid fail (outlet closed) must not count against Dash's SLA with the client. Short goal 1.1, 'segera setelah item sebelumnya'. Highest reach (Buku Warung, SwipeRX). Still needs a PRD and a fail-condition SOP (Tab 7).
XD-01 | Mithril / Driver App | X-dock 100% — shipment + route, last-mile, failed conditions | Get every cross-docking client fully onto the new app end-to-end: shipment + route assignment, last-mile coverage, and failed-condition handling. The umbrella short goal. | 5 | 3 | 80% | 3 |  | P0 | Sep | Short | In progress — needs PRD | Isumi Karina | TBC | — | Short goal #1 from the 31 Aug internal meeting ('x-dock 100%'). This is the parent effort: shipment + route works for every client, last-mile is covered, and failed conditions are captured (not silently re-created). Retry Shipment (XD-02) is its immediate follow-on (meeting item 1.1).
XD-07 | Mithril / Back Office | COD Phase 1 — reconciliation | Record and reconcile Cash-on-Delivery collected per shipment (Zalora). Reconciliation only — no payment-gateway link yet. | 3 | 2 | 90% | 1.5 |  | P0 | Sep | Side | Prototype + PRD ✓ | Isumi Karina | TBC | — | Whiteboard side quest #1. Active focus per the 28 Aug meeting: one engineer paused 'upload performance' to concentrate on COD, working to Albert's PRD. Prototype + PRD ready and scope is narrow, so it fits September. Phase 2 (payment-gateway QRIS auto-check) is XD-14.
XD-03 | Integration / Dash Link | New API integration platform — sandbox, API key, webhook, simulation | A reusable API integration capability so clients can integrate order intake — sandbox (auto-single-run), API keys, webhooks, developer mode — instead of one-off manual integrations. | 4 | 3 | 70% | 3.5 |  | P0 | Sep | Short | Prototype/simulation exists; timeline revising | Isumi Karina | TBC | Sandbox tech spec | Short goal #2 ('new api integration'), prioritized because API demand is urgent (31 Aug). Distinct from the cancelled NCS-specific integration — this is the general platform: sandbox focused on Dash Link, developer mode, GitHub repo, auto-run so API + UI run automatically. Prototype/simulation already exists; timeline being revised. Yogi = R&D / integration lead per the meeting (Engineer still TBC in the column). Spans Sep→Oct; sandbox spec is an open item (Tab 7).
XD-06 | Driver App (Mobile) | Multi-invoice per visit + scan blank document / leave at outlet | Driver handles multiple invoices in one outlet visit, plus a 'leave at outlet' option with a scanned blank-document (BAST) as proof. | 4 | 2 | 85% | 1.5 |  | P1 | Sep | Side | Prototype + PRD ✓ | Isumi Karina | TBC | Mobile engineer slot | Prototype + PRD ready and a mobile engineer picks it up Thursday 3 September — a clean September win. Whiteboard side quest #3 ('tinggal SJ'). Cuts failed-visit re-dispatch and matches how drivers work outlets.
XD-08 | Mithril | Timeline media download | Download media (proof photos) from the shipment timeline in Mithril, for client evidence sharing. | 3 | 1 | 70% | 0.5 |  | P2 | Sep | Side | None — needs PRD (small) | Isumi Karina | TBC | — | Whiteboard side quest #4 ('timeline media download → Mithril'), target ~9 September. Small; download proof media from the timeline. Schedule opportunistically inside September; low effort so it doesn't threaten the short-goal spine.
XD-05 | Back Office / Data | Master data — outlet goods-receiving hours (rider Google Form) | Reliable master data of each outlet's goods-receiving hours, to drive waiting-time and prioritization. | 3 | 2 | 75% | 1 |  | P1 | Oct | Short | None — needs process | Isumi Karina | TBC | — | 31 Aug: Google Maps scraping is inaccurate for receiving hours. Instead collect via a rider Google Form → spreadsheet → master data, focused on client outlets first. Low-effort and it unblocks XD-04, so high score. Mostly an Ops data-collection process + a small import.
XD-09 | Mithril / Driver App | Shipment Bypass Hub — SwipeRX | Rider rides the van from the Tempe warehouse straight to the pharmacy, bypassing the Dash hub. Uses Create Shipment with origin = client hub. | 3 | 2 | 80% | 1.5 |  | P1 | Oct | Side | Prototype ready | Isumi Karina | TBC | — | Prototype ready, status pending. SwipeRX-specific and not blocking any September launch, so October after the short-goal cluster.
XD-04 | Mithril / Dispatch | Remove 'Mark Stock' → configurable waiting-time-per-stop + outlet-hour prioritization | Ops shouldn't manage stock via 'Mark Stock'. Replace it with a per-client configurable waiting-time-per-stop and order prioritization driven by outlet operational hours. | 4 | 2 | 70% | 2 |  | P1 | Oct | Short | None — needs PRD | Isumi Karina | TBC | XD-05 (outlet-hours master data) | 31 Aug: 'Mark Stock' exists only because capacity is inaccurate, time is tight, and waiting-time-per-stop isn't modeled. Fix the root cause — configurable waiting time per stop (per client) + prioritize orders by outlet operational hours (whiteboard: outlet operational hour → waiting time per stop → clients). Removes a recurring Ops chore; depends on the outlet-hours master data.
XD-10 | Mithril | Filter client X-dock in Schedule menu | X-dock shares the Schedule calendar (default filter is Scheduled Instant); it needs a per-squad filter. The X-dock calendar stays empty until requirement gathering fills it. | 3 | 1 | 70% | 1 |  | P1 | Oct | Short | PRD partial — needs detail | Isumi Karina | TBC | — | Detail depends on requirement gathering that hasn't happened; low urgency next to the short-goal cluster, so October. The filter is small — the calendar content behind it is the real open question.
XD-11 | Mithril / Dash Link | Performance invoice — POV outlet | Invoice performance from the outlet's point of view (Logistic Mithril & Dash Link). Primarily a client request. | 3 | 1 | 85% | 1 |  | P2 | Oct | Side | Prototype + PRD ✓ (paused) | Isumi Karina | TBC | — | Ready but deliberately paused: per the meeting the engineer moved off 'upload performance' onto COD. Resume in October once COD Phase 1 is stable. Low reach (reporting view), so P2 despite being buildable.
XD-12 | Mithril / Ops | Transit antar-hub (inter-hub transit) | Route long-distance orders between hubs via scheduled transit: pickup region → back to hub → transit → deliver to destination. Run manually first. | 3 | 3 | 55% | 4 |  | P2 | Q4 | Med | Manual first — needs PRD | Isumi Karina | TBC | Dispatch schedule per hub | 31 Aug medium goal #1. Transit times morning/noon/night (morning & noon most important); tightly coupled to the dispatch schedule (e.g. dispatch 9am → transit must leave by 7am). Large coverage and scheduling-sensitive, so start manual and systematize later. Open risk: partners without an app keep transit manual — a mitra queueing tool is an open question (Tab 7).
XD-13 | Mithril / Driver App | Return dispatch / pickup (hub-to-hub) → feeds transit | Let a hub receive a shipment from a desk to another hub, and combine a drop + pickup in one driver trip. Feeds the inter-hub transit flow. | 3 | 2 | 50% | 2.5 |  | P2 | Q4 | Med | None — needs PRD | Isumi Karina | TBC | XD-12 (transit), Zalora return agreement (Business) | 31 Aug medium goal #2. Broader than the earlier Zalora dispatch+pickup: return dispatch/pickup lets a hub receive shipment from desk → another hub, which must align with the transit flow. The pickup-combine part still needs the Zalora return agreement (no negotiation started). Medium goal → Q4.
XD-14 | Mithril / Back Office + PG | COD Phase 2 — Payment Gateway QRIS auto-check | Connect COD to the Payment Gateway to auto-verify QRIS payment, replacing Phase 1's manual reconciliation. | 3 | 2 | 60% | 3 |  | P2 | Q4 | Side | None — needs PRD | Isumi Karina | TBC | XD-07 (Phase 1), PG integration | Builds on Phase 1. External payment-gateway dependency plus no PRD yet → confidence low and effort high, so Q4. Start only once Phase 1 reconciliation is live and the PG contract/scope is settled.

## 6. Push Notif Breakdown
4W Driver App — Push Notification Catalogue & Per-Notif Priority
Kept on its own tab. 2 waves. Wave 1 = trip-critical (blocks driver from acting) — ships Sep with the 4W P0 cluster. Wave 2 = supportive — Oct.
# | Notification | Trigger source | Recipient | Message template (ID) | Rationale | Priority | Wave
PN-01 | New shipment assigned | Mithril create → assignment | Driver | Shipment baru: {waybill} · {client} · {vehicle}. Ketuk untuk lihat detail. | Highest reach — every trip starts here. Today the driver only knows via WhatsApp from Ops. Removes the #1 Ops phone-call load. | P0 | Wave 1
PN-02 | Shipment cancelled | Mithril Cancel Shipment (NS-MTH-01) | Driver | Shipment {waybill} dibatalkan. Alasan: {reason}. | Prevents a driver executing a trip Ops just killed. Depends on Cancel Shipment (NS-MTH-01) landing first. | P0 | Wave 1
PN-03 | Ops marked shipment Completed / Failed | Mithril Mark as Completed/Failed (NS-MTH-02) | Driver | Shipment {waybill} ditandai {status} oleh Ops. Alasan: {reason}. | Closes the loop when Ops overrides in the phone-dead scenario. Driver knows not to retry. | P0 | Wave 1
PN-04 | Reminder: gate-pass wait timer running long | Server-side: ANTRI_GATE_PASS > threshold (e.g. 30 min) | Driver | Sudah {duration} menunggu gate pass. Foto antrian lagi kalau situasi berubah. | Gate-pass wait is billing evidence. Keeps evidence fresh & flags anomalies. | P1 | Wave 1
PN-05 | Workflow updated by Ops (edge — mid-trip) | Mithril workflow master update | Driver | Alur untuk {waybill} diperbarui. Buka ulang shipment untuk sinkron. | Edge case — freeze-on-create means in-flight trips shouldn't need this. Only fires if Ops force-refreshes. | P3 | Wave 2
PN-06 | Reminder: shipment inactive > 15 min mid-stop | Server-side: no proof submission for N minutes on active stop | Driver | Belum ada foto/aksi di {step}. Semua ok? | Catches a driver who forgot to submit (common cause of stuck IN_DELIVERY). Supportive nudge, not blocking. | P1 | Wave 2
PN-07 | Daily trip summary (07:00 WIB) | Server-side scheduled | Driver | Selamat pagi. Hari ini kamu punya {n} shipment. Ketuk untuk mulai. | Good-morning nudge — replaces the manual Ops WA broadcast. Relies on assignment being finalized the night before. | P2 | Wave 2

## 7. Open Questions
Open Questions & Decisions Needed
Unresolved items from the 28 & 31 Aug meetings that block or shape prioritized work. Resolve to unlock the linked items.
# | Question / decision | Area | Owner | Blocks | Needed by
OQ-01 | Fail-condition SOP + evidence format for Retry Shipment — full list of fail reasons and what proof each needs (e.g. photo of closed outlet). | X-dock | Product + Ops | XD-02 (Retry + SLA defense) | Early Sep
OQ-02 | Manpower split for short goals — who owns x-dock 100%, Retry, and the API platform; individual assignments. | All / X-dock | Leads (next meeting) | XD-01, XD-02, XD-03 land dates | Early Sep
OQ-03 | Sandbox technical spec + revised API timeline — scope, environment, auto-run pipeline; GitHub repo. | X-dock / Eng | Eng (Yogi, R&D) | XD-03 (API platform) | Sep
OQ-04 | Pricing per shift — commercial decision (dedicated manpower / daily-flat rates). | Scheduled Instant | Business (Pak Harina, Mon 1 Sep) | SI-02 (Pricing per shift) | 1 Sep
OQ-05 | Transit scheduling detail — exact transit times & frequency per hub; dispatch schedule alignment (e.g. dispatch 9am → transit by 7am). | X-dock | Ops | XD-12 (inter-hub transit) | Q4 scoping
OQ-06 | Mitra queueing tool — partners without an app; does Faktual Capital / HAPI / LASMAN replace the IT-Mitra role, or does transit stay manual? | X-dock | Business / IT | XD-12 (transit rollout) | Q4 scoping
OQ-07 | Zalora return agreement — commercial agreement for return dispatch/pickup (no negotiation started yet). | X-dock | Business | XD-13 (return dispatch/pickup) | Before Q4
OQ-08 | AI CSV upload feasibility — Speaker 1 to analyze NCS sample CSV template & logic; go/no-go on the AI header-checker. | Scheduled Instant | Product + Eng (Speaker 1) | SI-04 (AI spike path) | Sep
OQ-09 | UJP upload master-data sources — identify every source needed to upload UJP; integration with spec control & 'grounds'. | 4W | Eng + Ops | NS-MTH-04 (UJP native) | Q4 scoping
OQ-10 | 4W Ops input fields — confirm exact definition & source of DN Customer, FO, and AGL Route Code (validation rules, where they display). | 4W | Ops + Product | 4W-FLD (Ops input fields) | Early Sep